## Sheet1
Sl No | Date | Issues | Status | Comment | Update | Final Status _ Madhwa Team | Final Status _ Vindoh
1 | 2014-11-18 | Fortgot password missing in login page | Discussed with Vinod - PW will be sent to user registered mail id |  | Option is provided now in the login page. | Closed | Closed
2 | 2014-11-18 | Post login - User id should be shown on top right corner | Discussed with Vinod |  | User's fullname is placed on the top-right corner, which replaces the login/register links | Closed | Closed
3 | 2014-11-18 | User profile - Setting - Edit profile - Cancel button need to be renamed as reset | Discussed with Vinod |  | Aborts the changes done on the fields, and resets to the original values. | Closed | Closed
4 | 2014-11-18 | Admin Approvals were not working - | Discussed with Vinod - | Presently available version is working fine | The DB was out of sync. Now is working properly. | Closed | Closed
5 | 2014-11-18 | Details View for End user - Any end users data should not be shared with anyone. Only admin should have ability to see all kind of user details including service provider. | Discussed with Vinod |  | I have provided an option to turn off the visibility of the users of a usertype. If you enable this option for a particular usertype, then anyone other than admin logs in (or no one has logged in), can not see these users. | Closed | Closed
6 | 2014-11-18 | Messages - Blank messages are being sent | Discussed with Vinod |  | Fixed. | Closed | Closed
7 | 2014-11-18 | Service Request showing error message | Discussed with Vinod |  | Working on it now. | Closed | Closed
9 | 2014-11-19 | After Registration - Once the end user registers, a mail goes to his registered mail id. Is there any dependency on the user side to activate any link through the mail received from Madhwa connect? Presently what we see is, user can immediately logon to the website without any additional authentication. however for service provider, he need to wait till the Madhwa connect admin has to approve his request. | Discussed with Vinod |  | The users will not be listed, but they may login and update their profile details, while the admin has not approved yet. Once the admin approves them, then only they will be listed in the search results. | Closed | Closed
8 | 2014-11-19 | Login Screen - Once the user enters their id and pw and if he hits the ENTER key then he should be logged onto the website. However presently the user need to go the login button and then press the ENTER KEY. |  |  | Fixed. | Closed | Closed
11 | 2014-11-19 | Calendar Dates : Calendar dates are being blocked for the previous dates. For example, today date is 19th of Nov 2014. However the application should not allow service provider to block their previous dates. To be more precise, he should not be allowed to block 18th Nov 2014 date (in this case). |  |  | Updated such that, dates older than the current date will not be re-scheduled. | Closed | Closed
12 | 2014-11-19 | Legends required on calendar page - Top right corner, legends should be displayed as - RED for Booked & Green for availability |  |  | Done. | Closed | Closed
13 | 2014-12-21 | admin@madhwaconnect.com - Where to check these mails... Which id is this? Where we can find this | Discussed | webmail access: https://asia.login.secureserver.net/?app=wbe.ap admin@madhwaconnect.com Password: adMIN12#$ noreply@madhwaconnect.com Password: noREPLY12#$ Incoming server (POP3): pop.asia.secureserver.net Ports: 110, 995 (SSL) Outgoing server (SMTP): smtpout.asia.secureserver.net Ports: 80, 3535, 25, 465 (SSL) | Done | Closed | Closed
14 | 2014-12-21 | Service request demo required | Discussed |  | Done | Closed | Closed
15 | 2014-12-21 | Forget Password - Mails are not coming to respective mail id's | Discussed | Pending |  | Open | Closed
16 | 2014-12-21 | Terms & Condition Page should be static... No information should be displayed in that apart from terms and conditions | Discussed |  | Done | Closed | Closed
17 | 2014-12-21 | Register - After Pressing registration button - if there are error while filling details.. Eihter the page should go the error details button or an error message should be displayed next to register button. This will help the user to go the required field to fill the right details | Discussed |  | Done | Closed | Closed
18 | 2014-12-21 | When user goes to register page... We see advacne serach options... This should not be shown... The advace search should show only for the registerd users. | discussed |  | Done | Closed | Closed
19 | 2014-12-21 | Calendar window closer button required - Presently only escape works... | discussed |  | Done | Closed | Closed
20 | 2014-12-21 | Desired Name - after pressing tab... Cursor goes availability... If you press space bar... Page goes down... Suggestion here is - better space bar should be considered for checking name and enter button | discussed |  | Explained and agreed for no changes | Closed | Closed
21 | 2014-12-21 | user has logged onto the site... However when comes to home page... He will not come to know whether.. He is still logged in or logged out | discussed |  | Done | Closed | Closed
22 | 2014-12-21 | Login Page - Here also advance search should not be shown |  |  | Done | Closed | Closed
23 | 2014-12-25 | Went to Setting and try to upload the picture. Following error message received | Please see attached doc |  | Fixed. | Re-Open | Closed
24 | 2014-12-25 | Post this step I went to home page and clicked on service tab. After clicking this I see the message showing image is successfully uploaded. Here is the screen shot. | Please see attached doc |  | Fixed. | Re-Open | Closed
25 | 2014-12-25 | If user wants to change his picture, however the system is not taking the second picture. Please validate this functionality | Please see attached doc |  | Fixed. | Re-Open | Closed
26 | 2014-12-25 | Without login... Photo should not be displayed | Please see attached doc |  | Done | Closed | Closed
27 | 2014-12-25 | For the end user profile – Blocking of dates should not available. Is Calendar helpful for end user in settings? | Please see attached doc |  | Fixed by removing the "Calendar" menu item for endusers | Closed | Closed
28 | 2014-12-25 | After Registration for Cook, Purohit and Pandit - A message window shows | Please see attached doc |  | Fixed. |  | Closed
29 | 2014-12-25 | End User/Service Provider where there is no approval | Please see attached doc |  | Fixed. |  | Closed
30 | 2014-12-25 | User before logs in - Website shows some shows some data.. Let us show only fist 2 digits of the cell number. |  | Email - 4 letters of email + 10 '*'s Cellphone - 4 digits of cellphone + 6 '*'s |  |  | Closed
31 | 2014-12-25 | Administration Login - No option available to go home page |  |  | Fixed. |  | Closed
32 | 2014-12-25 | Dash Board - What other means |  | Discussed |  |  | Closed
33 | 2014-12-25 | Search Function seem to be issues - I created 2 id's hans1 (end user) and hans2 (purohit) ... When i type hans... I am not getting anything.. Even when we try for any kind of function... I am not getting any serach results... For example - when i type homa... i am not gettting any resutls |  | end user will not be listed. And service providers who needs admin approval, will not be listed until the admin approves. The search based on service/category terms is now fixed. | No issue/fixed |  | Closed
34 | 2014-12-25 | Cell No and LL number fileds should take only numeric numbers and not characters |  |  |  |  | OPEN
35 | 2014-12-25 | Login Page - There is no option for going to Home page... Need to have Home page link |  |  | Fixed. |  | Closed
36 | 2014-12-25 | Registration Page - There is no option for going to Home page... Need to have Home page link |  |  | Fixed. |  | Closed
37 | 2014-12-25 | All numeric fields should take only numbers entries - No of year experience and months and other fields... |  |  |  |  | OPEN
38 | 2014-12-25 | Delete option in administrator - User service and category. While deleting any category... Application should ask the user to confirm before deletion happens. Presently, once you press delete button.. Immediately get deleted |  |  | Done |  | Closed
39 | 2014-12-25 | Discussed in our conversatation - Pandit can also perfomr Purohit tasks... In this Pandit need to have all tasks mentioned in Purohit category.... Please explain |  | You have to add any/all services to each of the usertypes, whether it is same or different for another user. | There is no issue. |  | Closed
40 | 2014-12-25 | Statistics on no of site visits is still missing |  | As discussed, will be taken care by a third party website called "statcounter.com". It will be installed as a wordpress plugin. |  |  | OPEN
41 | 2014-12-25 | Address1 and Address2 field shows beyond the limit of page.... Please refer Mahan Rao user |  |  | Fixed |  | Closed
42 | 2014-12-25 | Edit Options for User Types and Categories in admin options - Services |  | See below |  |  | Closed
43 | 2014-12-25 | New Service created - Corresponding tasks were created accordingly. However those tasks are not show seperately. Please refer House Rent/Sale service - 1bhk,2bhk,3bhk. Here 1bhk, 2bhk, 3bhk is showing as one entry with one check box |  | While creating "New Category and Services", you should provide the list of services in separate line. Probably you had given the list of services in a comma separated values format. | There is no issue. |  | Closed
44 | 2014-12-26 | Login page - When user enter wrong password... No message as wrong pw or id...... Again login page is shown to user. However this was working correctly till yesterday. |  |  |  | Open | Closed
| 2014-12-26 | Picture Upload - After picuture uploads - Additional message comes at the bottom. |  |  |  | Open | Closed
2014-12-26