## 2014
Sl No | Date | Issues | Status | Comment | Update | Final Status _ Madhwa Team | Final Status _ Vinod
1 | 2014-11-18 | Fortgot password missing in login page | Discussed with Vinod - PW will be sent to user registered mail id |  | Option is provided now in the login page. | Closed | Closed
2 | 2014-11-18 | Post login - User id should be shown on top right corner | Discussed with Vinod |  | User's fullname is placed on the top-right corner, which replaces the login/register links | Closed | Closed
3 | 2014-11-18 | User profile - Setting - Edit profile - Cancel button need to be renamed as reset | Discussed with Vinod |  | Aborts the changes done on the fields, and resets to the original values. | Closed | Closed
4 | 2014-11-18 | Admin Approvals were not working - | Discussed with Vinod - | Presently available version is working fine | The DB was out of sync. Now is working properly. | Closed | Closed
5 | 2014-11-18 | Details View for End user - Any end users data should not be shared with anyone. Only admin should have ability to see all kind of user details including service provider. | Discussed with Vinod |  | I have provided an option to turn off the visibility of the users of a usertype. If you enable this option for a particular usertype, then anyone other than admin logs in (or no one has logged in), can not see these users. | Closed | Closed
6 | 2014-11-18 | Messages - Blank messages are being sent | Discussed with Vinod |  | Fixed. | Closed | Closed
7 | 2014-11-18 | Service Request showing error message | Discussed with Vinod |  | Working on it now. | Closed | Closed
9 | 2014-11-19 | After Registration - Once the end user registers, a mail goes to his registered mail id. Is there any dependency on the user side to activate any link through the mail received from Madhwa connect? Presently what we see is, user can immediately logon to the website without any additional authentication. however for service provider, he need to wait till the Madhwa connect admin has to approve his request. | Discussed with Vinod |  | The users will not be listed, but they may login and update their profile details, while the admin has not approved yet. Once the admin approves them, then only they will be listed in the search results. | Closed | Closed
8 | 2014-11-19 | Login Screen - Once the user enters their id and pw and if he hits the ENTER key then he should be logged onto the website. However presently the user need to go the login button and then press the ENTER KEY. |  |  | Fixed. | Closed | Closed
11 | 2014-11-19 | Calendar Dates : Calendar dates are being blocked for the previous dates. For example, today date is 19th of Nov 2014. However the application should not allow service provider to block their previous dates. To be more precise, he should not be allowed to block 18th Nov 2014 date (in this case). |  |  | Updated such that, dates older than the current date will not be re-scheduled. | Closed | Closed
12 | 2014-11-19 | Legends required on calendar page - Top right corner, legends should be displayed as - RED for Booked & Green for availability |  |  | Done. | Closed | Closed
13 | 2014-12-21 | admin@madhwaconnect.com - Where to check these mails... Which id is this? Where we can find this | Discussed | webmail access: https://asia.login.secureserver.net/?app=wbe.ap admin@madhwaconnect.com Password: adMIN12#$ noreply@madhwaconnect.com Password: noREPLY12#$ Incoming server (POP3): pop.asia.secureserver.net Ports: 110, 995 (SSL) Outgoing server (SMTP): smtpout.asia.secureserver.net Ports: 80, 3535, 25, 465 (SSL) | Done | Closed | Closed
14 | 2014-12-21 | Service request demo required | Discussed |  | Done | Closed | Closed
15 | 2014-12-21 | Forget Password - Mails are not coming to respective mail id's | Discussed | Pending |  | Open | Closed
16 | 2014-12-21 | Terms & Condition Page should be static... No information should be displayed in that apart from terms and conditions | Discussed |  | Done | Closed | Closed
17 | 2014-12-21 | Register - After Pressing registration button - if there are error while filling details.. Eihter the page should go the error details button or an error message should be displayed next to register button. This will help the user to go the required field to fill the right details | Discussed |  | Done | Closed | Closed
18 | 2014-12-21 | When user goes to register page... We see advacne serach options... This should not be shown... The advace search should show only for the registerd users. | discussed |  | Done | Closed | Closed
19 | 2014-12-21 | Calendar window closer button required - Presently only escape works... | discussed |  | Done | Closed | Closed
20 | 2014-12-21 | Desired Name - after pressing tab... Cursor goes availability... If you press space bar... Page goes down... Suggestion here is - better space bar should be considered for checking name and enter button | discussed |  | Explained and agreed for no changes | Closed | Closed
21 | 2014-12-21 | user has logged onto the site... However when comes to home page... He will not come to know whether.. He is still logged in or logged out | discussed |  | Done | Closed | Closed
22 | 2014-12-21 | Login Page - Here also advance search should not be shown |  |  | Done | Closed | Closed
23 | 2014-12-25 | Went to Setting and try to upload the picture. Following error message received | Please see attached doc |  | Fixed. | Closed | Closed
24 | 2014-12-25 | Post this step I went to home page and clicked on service tab. After clicking this I see the message showing image is successfully uploaded. Here is the screen shot. | Please see attached doc |  | Fixed. | Closed | Closed
25 | 2014-12-25 | If user wants to change his picture, however the system is not taking the second picture. Please validate this functionality | Please see attached doc |  | Fixed. | Closed | Closed
26 | 2014-12-25 | Without login... Photo should not be displayed | Please see attached doc |  | Done | Closed | Closed
27 | 2014-12-25 | For the end user profile – Blocking of dates should not available. Is Calendar helpful for end user in settings? | Please see attached doc |  | Fixed by removing the "Calendar" menu item for endusers | Closed by vinod on 27/12/2014 | Closed
28 | 2014-12-25 | After Registration for Cook, Purohit and Pandit - A message window shows - Please display information which is provided in the document | Please see attached doc |  | Fixed. | Closed by vinod on 27/12/2014 | Closed
29 | 2014-12-25 | End User/Service Provider where there is no approval - Same as above | Please see attached doc |  | Fixed. | Closed | Closed
30 | 2014-12-25 | User before logs in - Website shows some shows some data.. Let us show only fist 2 digits of the cell number. |  | Email - 4 letters of email + 10 '*'s Cellphone - 4 digits of cellphone + 6 '*'s |  | Closed | Closed
31 | 2014-12-25 | Administration Login - No option available to go home page |  |  | Fixed. | Closed | Closed
32 | 2014-12-25 | Dash Board - What other means |  | Discussed |  | Closed | Closed
33 | 2014-12-25 | Search Function seem to be issues - I created 2 id's hans1 (end user) and hans2 (purohit) ... When i type hans... I am not getting anything.. Even when we try for any kind of function... I am not getting any serach results... For example - when i type homa... i am not gettting any resutls |  | end user will not be listed. And service providers who needs admin approval, will not be listed until the admin approves. The search based on service/category terms is now fixed. | No issue/fixed | Closed | Closed
34 | 2014-12-25 | Cell No and LL number fileds should take only numeric numbers and not characters |  |  |  | Open | Closed
35 | 2014-12-25 | Login Page - There is no option for going to Home page... Need to have Home page link |  |  | Fixed. | Closed | Closed
36 | 2014-12-25 | Registration Page - There is no option for going to Home page... Need to have Home page link |  |  | Fixed. | Closed | Closed
37 | 2014-12-25 | All numeric fields should take only numbers entries - No of year experience and months and other fields... |  |  |  | Open | Closed
38 | 2014-12-25 | Delete option in administrator - User service and category. While deleting any category... Application should ask the user to confirm before deletion happens. Presently, once you press delete button.. Immediately get deleted |  |  | Done | Closed | Closed
39 | 2014-12-25 | Discussed in our conversatation - Pandit can also perfomr Purohit tasks... In this Pandit need to have all tasks mentioned in Purohit category.... Please explain |  | You have to add any/all services to each of the usertypes, whether it is same or different for another user. | There is no issue. | Closed | Closed
40 | 2014-12-25 | Statistics on no of site visits is still missing |  | To check the visit details, login to http://statcounter.com with username as madhwaconnect and password admin123 Then goto this link to see data: http://statcounter.com/p10204885/summary/ You can also see the data from within our website at this URL: http://madhwaconnect.com/wp-admin/index.php?page=statcounter |  | Open | Closed
41 | 2014-12-25 | Address1 and Address2 field shows beyond the limit of page.... Please refer Mahan Rao user |  |  | Fixed | Closed | Closed
42 | 2014-12-25 | Edit Options for User Types and Categories in admin options - Services |  | See below |  | Closed | Closed
43 | 2014-12-25 | New Service created - Corresponding tasks were created accordingly. However those tasks are not show seperately. Please refer House Rent/Sale service - 1bhk,2bhk,3bhk. Here 1bhk, 2bhk, 3bhk is showing as one entry with one check box |  | While creating "New Category and Services", you should provide the list of services in separate line. Probably you had given the list of services in a comma separated values format. | There is no issue. | Closed | Closed
44 | 2014-12-26 | Login page - When user enter wrong password... No message as wrong pw or id...... Again login page is shown to user. However this was working correctly till yesterday. |  |  |  | Closed | Closed
45 | 2014-12-26 | Picture Upload - After picuture uploads - Additional message comes at the bottom. |  |  |  | Closed | Closed
46 | 2014-12-27 | Advanced search - Date format - should be ddmmyyyy |  |  |  | Open | Closed
47 | 2014-12-27 | New Message - Count should be displayed in the tool bar |  |  |  | Open | Closed
48 | 2014-12-27 | Registration Page - Mandatory fields should be marked with red color (*) |  |  |  | Open | Closed
49 | 2014-12-27 | Matha - Mutt - Additional details while registering.. This should be displayed as Mutt whereever it is mentioned as Mutha |  |  |  | Open | Closed
50 | 2014-12-27 | Service Request - Button "Create Request" should be renamed as "Send Request" |  |  |  | Open | Closed
51 | 2014-12-27 | while sending messages getting err (OOOPS) |  |  |  | Open | Closed
52 | 2015-01-01 | In Search windown, if you type service offered (word), application does not show any results. Fox example - if you type purohit... I do not get any results. However when i type cook... I am getting only one record for cook. By default it is considering Mohan Rao cook |  |  |  | Open | Closed
53 | 2015-01-01 | Service provide once he registers... 1) He is able to login even without approval from admin. This is not be case. All service provider should be able to login once it is approved by the admin 2) Service provider without approval is able to send message to groups. This should not be the case |  | Service providers will be able to login, but will not be listed in the search results. Hence they can not be contacted by any other users. The reason why even before approval they can login is to make any updations to their profile, in case if they have not done so. For example, if a cook has not mentioned his mutt or gotra, admin can ask him to update the profile with these details. If login is not allowed until approval, then admin has to approve first before the cook can updated the profile. |  | Open | Closed
54 | 2015-01-01 | Service Request - When a service provider sends message to the same category (serivce provider - for example - cook to cook)... Message is getting delivered to the individual who has sent this message. |  | Service request is like a bulletin board. A service requested by a user (usually enduser) for a particular category (eg cook) will be shown to each of the cooks (not as messages). If any of the cooks are interested, they can browse for available service requests, and if they feel they can take up the assignment, they can respond to that particular service request. From here, there will be new message thread between the user who posted the service request and the service provider who is responding to the same. |  | Open | Closed
55 | 2015-01-01 | Message created date is still showing yyyy-mm-dd. Please ensure that dd-mm-yyyy format is followed acorss all the date formats |  |  |  | Open | Closed
56 | 2015-01-01 | new message count should be on the menu bar - Presently it is showing in unread message.... |  |  |  | Open | Closed

## 2015
Sl No | Date | Issues | Status | Comment | Update | Final Status _ Madhwa Team | Final Status _ Vinod
1 | 2015-01-06 | Message - From Admin - Though message does not go to users, however it shows count in the message box | Discussed with Vinod |  |  |  | Closed
2 | 2015-01-06 | Edit Profile - Service provider does not have option of editing their service options. Presently it is available only for their personal information updates | Discussed with Vinod |  |  |  | Closed
3 | 2015-01-06 | Edit Profile - Validations are missing - even if a user updates the field with blank.. Application gets updated with blank data. Same kind of validation should be applied which are available in registration page | Discussed with Vinod | Do not chage anything as of now. Keep it on hold. |  |  | Open
4 | 2015-01-06 | Global notification from admin to all user and also to the selected group | Discussed with Vinod | This option is required if admin would like to send a global communication to entire users and service provider. Also it should have a option of sending to one single group as well |  |  | Closed
5 | 2014-12-02 | Madhwaconnect Outlook - Not able to send mails from outlook. Only we are able to receive mails | Discussed with Vinod | Need Immediate Attention |  |  | Closed
6 | 2015-01-06 | Restriction of picture size to 1mb and provide a message "Picture Size is more and please reduce the size and reload" | Discussed with Vinod | Need Immediate Attention |  |  | Closed
7 | 2015-01-16 | Admin Login - In View Profile - additional Information Is Not Displayed |  |  |  |  | Closed
8 | 2015-01-16 | Address Field Should be made mandatory |  | "Address line1" changed to "Address" and "Address line2" changed to "Area" in the registration page |  |  | Closed
9 | 2015-01-16 | Area field need to newly inserted |  | "Address line1" changed to "Address" and "Address line2" changed to "Area" in the registration page |  |  | Closed
10 | 2015-01-16 | On Registration page, tool should allow to upload photo for everyone |  |  |  |  | Closed
11 | 2015-01-16 | After Logout, home page should be displayed |  |  |  |  | Closed
12 | 2015-01-16 | In Login mode and comining to home page. After this user wants to go back to Service page, he does not have single click go back the Previus page. This should be anabled on the welcome button. |  |  |  |  | Closed
13 | 2015-01-17 | After coming to service - view profile page - A scrolling message should appear "To view complete details - Please login or Register" |  |  |  |  | Closed
14 | 2015-01-29 | 1) Images does not show - |  | There was a bug, and I have fixed it now. Gone through all images as of now, and it seems to be working. |  |  | Closed
15 | 2015-01-29 | 2) 1st entry is not sorted by alphbatically |  |  |  |  | Closed
16 | 2015-01-29 | 3) Can we have photo displayed on in view profile. This will help to show many entries on one page |  | Discussed with the team, and concluded to ignore this |  |  | Closed
17 | 2015-01-29 | 4) Advanced should be renamed as advaced search |  |  |  |  | Closed
18 | 2015-01-29 | 5) Can we display advanced search - on service/view profile page |  | Discussed with the team, and concluded to ignore this |  |  | Closed
19 | 2015-01-29 | 6) Service provider - Mandatory atleast one service should be selected |  |  |  |  | Closed
20 | Taken from Log Tab | Area need to added |  | "Address line1" changed to "Address" and "Address line2" changed to "Area" in the registration page |  |  | Closed
21 | Taken from Log Tab | Area & City to mandatory |  | Done. |  |  | Closed
22 | Taken from Log Tab | Mail id and user id to aligned |  | Did not understand where exactly the problem. Can you be little more specific? The user id is never displayed anywhere. |  |  | Open
23 | Taken from Log Tab | Address not be shown |  | Full address not shown now. Only city, state and country displayed. This was as per our previous telephonic discussion. |  |  | Closed
24 | Taken from Log Tab | Photo down load and update from Admin |  | You can login using the administrator password as any user. The username should be of the format XXXX:administrator where XXXX can be username, email or another_email of the user you want to login as. |  |  | Closed
25 | Taken from Log Tab | Admin - Super Access |  |  |  |  | Closed
26 | 2015-02-05 | Disabling the approved service provider |  | As administrator, you can search for any registered member, and view full profile and see a button "Suspend User". When you suspend a user, an email will goto that user informing that his account is suspended. The user will not be able to login. Administrator can once again search for the same user and view full profile. This time, the button will say "Restore user". On restoring the user account, user will get another mail (approval mail) and will be able to login with the same password. |  |  | Closed
27 | 2015-02-05 | Disabling the end user. |  |  |  |  | Closed
28 | 2015-02-05 | In one user type under a category there are already few services. Now we need to add additional services to the same category. This option is not available for Admin |  | You must delete the category and add it once again. Adding is easy since you just have to give a list of service. This we had discussed over phone in our previous discussion |  |  | Closed
29 | 2015-02-05 | Menu Option - Religious Services and Value Added Services. Admin should have ability to classify for future entries |  | As administrator, you can specify if a usertype is "Relegious" or "Value added". I have categorized all users except "Photo/Video grapher" as "Relegious". The menu shows "Services" under which, you may see "All, Relegious, Value added". "Relegious" and "Value added" show the specificy user types under each group. |  |  | Closed

## Log
User login - Edit option for service is not be shown
Area need to added
Area & City to mandatory
Mail id and user id to aligned
Address not be shown
Photo down load and update from Admin
Admin - Super Access